## bySize
TSHIRT | %tage | Number of features | Number of Sprints BEST CASE | Number of Sprints MOST LIKELY | Number of Sprints WORST CASE
Zero | 0% | 3 | 0 | 0 | 0
XXSmall | 2.439% | 3 | 0.36875 | 0.375 | 0.38125
XSmall | 6.504% | 4 | 0.925 | 1 | 1.075
Small | 13.01% | 4 | 1.75 | 2 | 2.25
Medium | 39.02% | 6 | 4.75 | 6 | 7.25
Large | 39.02% | 3 | 3.9 | 6 | 8.1
Total | 100% | 23 | 11.6937 | 15.375 | 19.0562
s

## byUncertainty
Business Uncertainty / Size | %tage | Number of Sprints BEST CASE | Number of Sprints MOST LIKELY | Number of Sprints WORST CASE
Low | 25.2% | 3.275 | 3.875 | 4.475
Zero | 0% | 0 | 0 | 0
XXSmall | 0.813% | 0.125 | 0.125 | 0.125
XSmall | 1.626% | 0.25 | 0.25 | 0.25
Small | 3.252% | 0.5 | 0.5 | 0.5
Medium | 6.504% | 1 | 1 | 1
Large | 13.01% | 1.4 | 2 | 2.6
Medium | 28.46% | 3.525 | 4.375 | 5.225
High | 46.34% | 4.8937 | 7.125 | 9.3563
Total | 100% | 11.6937 | 15.375 | 19.0562

## byComplexity
Technical Complexity / Size | %tage | Number of Sprints BEST CASE | Number of Sprints MOST LIKELY | Number of Sprints WORST CASE
Low | 49.59% | 6.475 | 7.625 | 8.775
Medium | 25.2% | 2.475 | 3.875 | 5.275
High | 25.2% | 2.7437 | 3.875 | 5.0062
Total | 100% | 11.6937 | 15.375 | 19.0562

## Cone of Uncertainty
| X | Y
Best Case | 0 | 0 | Note: Labels added manually.
| 11.6938 | 10
Most Likely | 0 | 0
| 15.375 | 10
Worst Case | 0 | 0
| 19.0562 | 10
Threshold | 0 | 10
| 20.375 | 10
Threasheold | 10
Length of threshold | 5

## Features_report
ID | Summary | Description | TSHIRT | Business Uncertainty | Technical Complexity | BEST CASE | MOST LIKELY | WORST CASE | Epic/Theme | CONE_UNCERT
1 | Feature 1 |  | XXSmall | Low | Low | 0.125 | 0.125 | 0.125 |  | 0
2 | Feature 2 |  | XSmall | Low | Low | 0.25 | 0.25 | 0.25 |  | 0
3 | Feature 3 |  | Small | Low | Low | 0.5 | 0.5 | 0.5 |  | 0
4 | Feature 4 |  | Medium | Low | Low | 1 | 1 | 1 |  | 0
5 | Feature 5 |  | Large | Low | High | 1.4 | 2 | 2.6 |  | 0.3
6 | Feature 6 |  | Zero | Low | Low | 0 | 0 | 0 |  | 0
7 | Feature 7 |  | XXSmall | Medium | Medium | 0.125 | 0.125 | 0.125 |  | 0
8 | Feature 8 |  | XSmall | Medium | High | 0.225 | 0.25 | 0.275 |  | 0.1
9 | Feature 9 |  | Small | Medium | High | 0.4 | 0.5 | 0.6 |  | 0.2
10 | Feature 10 |  | Medium | Medium | Low | 0.85 | 1 | 1.15 |  | 0.15
11 | Feature 11 |  | Large | Medium | Low | 1.5 | 2 | 2.5 |  | 0.25
12 | Feature 12 |  | Zero | Medium | Medium | 0 | 0 | 0 |  | 0
13 | Feature 13 |  | XXSmall | High | High | 0.11875 | 0.125 | 0.13125 |  | 0.05
14 | Feature 14 |  | XSmall | High | Low | 0.225 | 0.25 | 0.275 |  | 0.1
15 | Feature 15 |  | Small | High | Low | 0.425 | 0.5 | 0.575 |  | 0.15
16 | Feature 16 |  | Medium | High | Medium | 0.7 | 1 | 1.3 |  | 0.3
17 | Feature 17 |  | Large | High | Medium | 1 | 2 | 3 |  | 0.5
18 | Feature 18 |  | XSmall | High | Medium | 0.225 | 0.25 | 0.275 |  | 0.1
19 | Feature 19 |  | Zero | High | High | 0 | 0 | 0 |  | 0
20 | Feature 20 |  | Small | Medium | Medium | 0.425 | 0.5 | 0.575 |  | 0.15
21 | Feature 21 |  | Medium | High | Low | 0.8 | 1 | 1.2 |  | 0.2
22 | Feature 22 |  | Medium | High | Low | 0.8 | 1 | 1.2 |  | 0.2
23 | Feature 23 |  | Medium | High | High | 0.6 | 1 | 1.4 |  | 0.4
[6 empty] | 11.6938 | 15.375 | 19.0562

## SETUP
Sprints | TShirt Sizing | Business Uncertainty M | Business Uncertainty H | Sprints per TShirt Size Values |  | Business Uncertainty Values | Technical Complexity Values
0 | Zero | 0% | 0% | Zero | 0 | Low | Low
0.125 | XXSmall | 0% | 5% | XXSmall | 0.125 | Medium | Medium
0.25 | XSmall | 5% | 10% | XSmall | 0.25 | High | High
0.5 | Small | 10% | 15% | Small | 0.5
1 | Medium | 15% | 20% | Medium | 1
2 | Large | 25% | 35% | Large | 2
4 | Xlarge | 40% | 50% | XLarge | 4
Sprints | T-Shirt Sizing | Technical Complexity M | Technical Complexity H
0 | Zero | 0% | 0%
0.125 | XXSmall | 0% | 0%
0.25 | XSmall | 0% | 5%
0.5 | Small | 5% | 10%
1 | Medium | 10% | 20%
2 | Large | 15% | 30%
4 | XLarge | 20% | 40%
Sprints | T-Shirt Sizing | Technical Complexity M | Technical Complexity H
0 | Zero | 0% | 0%
0.125 | XXSmall | 0% | 0%
0.25 | XSmall | 0% | 5%
0.5 | Small | 5% | 10%
1 | Medium | 10% | 20%
2 | Large | 15% | 30%
4 | XLarge | 20% | 40%